## Sheet1
任务编号 | 技术治理单号 |  | SQL语句 | 备用字段1 | 备用字段2 | 备用字段3 | 备用字段4 | 是否申请例外 | 例外原因 | 修复情况 | 应用场景 | 代码位置 | 问题分析 | 系统开关 | 开发人员 | 计划完成时间 | 实际完成时间 | 完成标识 | 完成状态 | 完成方式 | 进展百分比(%) | 关联单号 | 治理方案 | 备注说明 | 填报标识 | 填报倒计时 | 自排倒计时 | 实际填报时间 | 更新时间 | 申请人 | 申请类型 | 原因类别 | 例外有效期 | 例外整改时机说明 | 具体原因 | 申请时间 | 任务启动时间 | 任务计划填报截止时间 | 任务计划截止时间 | 任务级别 | 任务类别 | 任务来源 | 任务标签 | 紧急程度 | 重要程度 | 考核标识 | 任务完成时限类别 | 关联故障 | 任务管理人 | 任务管理人所属部门
JSZL-202512220001-001694 | JSZL-202512220001 | 指令表 | SELECT ( WITH BASE_INSTRUCTION AS (SELECT Z.INSTRUCTION_ID, CASE WHEN (Z.SOURCE_ID IN (?, ?, ?, ?, ?) AND Z.PAYMENT_TYPE_ID IN (?, ?)) THEN NVL((SELECT CASE WHEN RTGS.SHCH_STOP_STATUS = ? THEN ? ELSE RTGS.SHCH_DRAW_STATUS END ¦¦ ? ¦¦ RTGS.SHCH_DRAW_STATUS FROM RTGS_COLLECTION_RECORD_1 RTGS WHERE RTGS.INSTRUCTION_ID = Z.INSTRUCTION_ID), ?) WHEN (Z.SOURCE_ID IN (?, ?, ?, ?, ?) AND Z.PAYMENT_TYPE_ID IN (?, ?)) THEN NVL((SELECT C.CCDC_DRAW_STATUS FROM CCDC_COLLECTION_RECORD C WHERE C.INSTRUCTION_ID = Z.INSTRUCTION_ID), ?) WHEN (Z.SOURCE_ID IN (?, ?, ?) AND Z.PAYMENT_TYPE_ID IN (?, ?)) THEN Z.DIRECT_STATUS WHEN (Z.PAYMENT_TYPE_ID = ?) THEN NVL((SELECT INSTRUCTION_PARAM_VALUE FROM INSTRUCTION_EXT WHERE INSTRUCTION_ID = Z.INSTRUCTION_ID AND INSTRUCTION_PARAM_NAME = ?), ?) ELSE ? END AS SHCHDRAWSTATUS, Z.PRODUCT_ID, Z.REALTIME_STATUS REALTIME_STATUS, Z.USE_ID, Z.PAYMENT_DATE, Z.PAYMENT_AT, Z.SUCCESSFUL_PAID_AT, Z.PAYMENT_TYPE_ID, (SELECT PT.PAYMENT_TYPE_NAME FROM PAYMENT_TYPE PT WHERE PT.PAYMENT_TYPE_ID = Z.PAYMENT_TYPE_ID) HKMC, Z.DIRECTION, Z.AMOUNT, Z.SOURCE_ID, Z.PAYMENT_REASON, Z.DEBIT_ACCOUNT, Z.DEBIT_ACCOUNT_NAME, Z.CREDIT_ACCOUNT, Z.CREDIT_ACCOUNT_NAME, Z.BANK_ID, Z.BANK_NAME, Z.DB_STATUS, Z.ANO_SYS_STAT, Z.BATCH, Z.IPO_SUBSCRIBE, Z.ENTRUST, Z.SECURITY_CODE, Z.PAYMENT_MODE, Z.INTER_BANK, DECODE(Z.FINAL_PAYMENTSTATUS, ?, ?, Z.FINAL_PAYMENTSTATUS) AS FINALSTATUSORDER, Z.FINAL_PAYMENTSTATUS, Z.PAYMENT_STATUS, (SELECT IP.YHMC FROM IP_STAFF_STMT IP WHERE IP.YHBH = Z.UPDATED_BY) UPDATEDBYNAME, Z.UPDATED_AT, Z.CREATED_AT, (SELECT IP.YHMC FROM IP_STAFF_STMT IP WHERE IP.YHBH = Z.INSTR_JBR) INSTR_JBR, (SELECT IP.YHMC FROM IP_STAFF_STMT IP WHERE IP.YHBH = Z.INSTR_FHR) INSTR_FHR, Z.FBANK_ID, Z.FBANK_NAME, Z.FDQH, Z.FJGH, Z.SDQH, Z.SJGH, Z.POST_ROUTE, Z.INSTRUC_BATCH, (SELECT W.WFNAME FROM WORKFLOW W WHERE W.WFID = Z.WFID) GZLMC, Z.SAME_CITY, Z.ZYZXRETFAXTIME, Z.ZYZXRETMSG, Z.ZYZXBZ, Z.INSTRUC_BATCH_FLAG, Z.ACTIVITY_CENTER_STATUS, Z.ACTIVITY_CENTER_FLAG, Z.ACTIVITY_CENTER_MESSAGE, NVL(Z.FAXPUSHTIME, Z.CREATED_AT) FAXPUSHTIME, Z.IS_EMERGENCY_PAYMENT, Z.TIMESTAMP, Z.PRIORITY, Z.SHOWCOMEACCOUNT, Z.PAYMENTWAY, Z.MESSAGE, Z.WHETHER_PASS_AUXILIARY, Z.TRADE_TYPE, Z.CORE_MSG, Z.CURRENCY BZ, Z.EXPORT_FLAG, Z.INSTRUCTION_TYPE, Z.ACTION_STATUS, Z.INSTRUCTION_MODEL, Z.DEAL_ORG_NO, (SELECT JGMC FROM IP_UNIT WHERE ZJ = Z.DEAL_ORG_NO) DEAL_ORG_NO_NAME, Z.CUST_CANCEL_STATUS, Z.CUST_PRD_CODE, Z.CUST_PRD_NAME, Z.OUT_ORG_NO, (SELECT JGMC FROM IP_UNIT WHERE ZJ = Z.OUT_ORG_NO) OUT_ORG_NO_NAME, Z.OUT_INSTRUCTION_ID, Z.SUMMARY ZYSM, (SELECT | 平均耗时(s)：14.32 | 执行次数：220 | 总耗时(s)：3151.28 | 监测时间：2026-06-01~2026-06-07 |  |  | 计划7.9版本修复 | 指令流程查询页面：查询普通指令的数量 | com.cib.settlement.hkgl.zlcx.dao.IInstructionQueryDao.findAllInfosForPtNewYHCount1 |  | findAllInfosForPtCount_v4.14.1 | 覃淞俊 | 2026-07-17 |  | 按期开展中 | 未开始 |  | 0 |  |  | 同JSZL-202512220001-000759 | 按期填报 |  | 25天后截止 | 2026-06-10 14:34:29 | 2026-06-16 19:00:51 | [7 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-001243 | JSZL-202512220001 | 指令表 | SELECT COUNT(?) FROM (SELECT I.*, TRUNC(NVL(I.PAYMENT_AT, I.PAYMENT_DATE)) AS IDX1, DECODE(I.DIRECTION, ?, I.CREDIT_ACCOUNT, ?, I.DEBIT_ACCOUNT) AS IDX2 FROM INSTRUCTION I WHERE I.PAYMENT_STATUS != ? AND ((I.SOURCE_ID = ? AND I.ACTION_STATUS = ?) OR I.ACTION_STATUS IN (?, ?, ?, ?, ?, ?, ?, ?, ?)) AND (I.FINAL_PAYMENTSTATUS IS NULL OR I.FINAL_PAYMENTSTATUS != ?)) I WHERE I.IDX1 = TO_DATE(:1 , ?) AND I.IDX2 = :2 | 平均耗时(s)：10.83 | 执行次数：182 | 总耗时(s)：1971.28 | 监测时间：2026-04-27~2026-05-03 |  |  | 计划7.9版本修复 | 共用账户日终页面：日终核对时获取未支付指令数量 共用账户日切页面：日切核对时获取未支付指令数量 | com.cib.settlement.rzrq.daycutdeal.dao.IDayCutDealDao.getUnpaidInstructionOpt、com.cib.settlement.rzrq.sharedaccountdayend.dao.ISharedAccountDayEndDao.getUnpaidInstructionOpt | 未命中索引，确保支付日期不为空，直接使用payment_at=即可 | getUnpaidInstructionOpt_v4.14.1 | 覃淞俊 | 2026-07-30 |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 按期填报 |  | 38天后截止 | 2026-05-07 11:43:29 | 2026-06-11 14:16:38 | [7 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-001051 | JSZL-202512220001 | 指令表 | SELECT * FROM ( SELECT ROW_.*, ROWNUM AS ROWNUM_ FROM ( WITH INSTRUCTION_DATA AS ( SELECT INSTRUCTION_ID,PRODUCT_ID,PAYMENT_DATE,PAYMENT_TYPE_ID,DIRECTION,AMOUNT,PAYMENT_REASON,SOURCE_ID,CREDIT_ACCOUNT,CREDIT_ACCOUNT_NAME,DEBIT_ACCOUNT,DEBIT_ACCOUNT_NAME,BANK_ID,BANK_NAME,BATCH,ENTRUST,IPO_SUBSCRIBE,WFID,WFSID,ITERATIONID,POSITION,P_INSTRUCTION_ID,PAYMENT_STATUS,ACTION_STATUS,PAYMENT_MODE,PAYMENT_AT,INTER_BANK,SAME_CITY,MESSAGE,CREATED_AT,CREATED_BY,UPDATED_AT,UPDATED_BY,INSTRUCTION_TYPE,CONCENTRATE_STATUS,VALIDATED_BY,USE_ID,PLUSTYPE,OUT_INSTRUCTION_ID,SECURITY_CODE,FBANK_ID,FBANK_NAME,FDQH,FJGH,SDQH,SJGH,DB_PRODUCT_ID,REALTIME_STATUS,PARENT_INSTRUCTION_ID,CREDIT_ACCT_TYPE_ID,DEBIT_ACCT_TYPE_ID,CREDIT_ACCOUNT_ID,DEBIT_ACCOUNT_ID,CURRENCY,WITHDRAW,VOUCHER,BUSINESS_TYPE,CASH,CREDIT_CARD,POST_ROUTE,PAYMENT_LEVEL,BUSINESS_SUBJECT,SUMMARY,CUSTOM_TYPE,BUSINESS_CATEGORY,CHANNEL,ACCOUNT_VOUCHER,ACCOUNT_PASSWORD,FUTHER_CODE,FUTHER_PASSWORD,CORE_INTERFACE,COUNTER_CASHFLOW,QSXWH,WXFXZYXX,INTERFACE_CODE,HSBZ,SUB_TYPE_ID,MESSAGE_V,ZQZH,ZQDM,RETURN_MSG,AUTOPAY,TRADE_TYPE,INSTR_GEN_SOURCE,ENTERACCOUNT_FLAG,LOCK_STATUS,ROLE_ID,CORE_MSG,FINAL_PAYMENTSTATUS,ZTCZFJG,LDSJMS,KH_PAYMENTSTATUS,CORE_INSTRUCTION_TYPE,CFCS,BEIYONG1,ZLSCFSJ,SHOWCOMEACCOUNT,PAYMENTWAY,FAXPUSHTIME,NEXTDATEINSTRUCTIONID,INSTRUC_BATCH,INSTRUC_BATCH_FLAG,INSTRUC_BATCH_SUM,INSTRUC_BATCH_DETAIL,USER_SUBSIDIARY_ORGAN,ZYZXRETFAXTIME,ZYZXRETMSG,ZYZXBZ,ACTIVITY_CENTER_STATUS,ACTIVITY_CENTER_FLAG,ACTIVITY_CENTER_MESSAGE,YWLSH,ZJTZZH,QHGSDM,INSTR_JBR,INSTR_FHR,BATCHINSNO,SUCCESSFUL_PAID_AT,PAY_LOCK_STATUS,PAY_LOCK_USER,REMARK,TGT_QDZLBH,AUTO_REMARK,IS_EMERGENCY_PAYMENT,TIMESTAMP,DISCARD_FLAG,PRIORITY,DB_STATUS,WHITE_FLGE,MZBZ,EXPORT_FLAG,PROIORITY_SUB,CSDS_BUSINESS_TYPE,WHETHER_PASS_AUXILIARY,AUXILIARY_ACCOUNT,VIRTUAL_PRODUCT_NAME,DEAL_ORG_NO,INSTRUCTION_MODEL,OUT_ORG_NO,CUST_PRD_CODE,CUST_CANCEL_STATUS,CUST_PRD_NAME,MANAGER_ID,PAYFLG,CORE_INSTRUCTION_ID,DFKSSJ,SUPERVISION_SIGN,SUPERVISORY_OPINION,INSTRUC_CONTACTS,DIRECT_STATUS,ANO_SYS_STAT,ARCHIVED_STATUS,ARCHIVED_RESULT,ARCHIVED_DATE,ARCHIVED_PACKAGE, CASE WHEN INSTRUCTION_ID LIKE ? THEN TO_DATE(? ¦¦ SUBSTR(INSTRUCTION_ID, ?, ?), ?) WHEN INSTRUCTION_ID LIKE ? THEN TO_DATE(SUBSTR(INSTRUCTION_ID, ?, ?), ?) WHEN INSTRUCTION_ID LIKE ? THEN TO_DATE(SUBSTR(INSTRUCTION_ID, ?, ?), ?) WHEN INSTRUCTION_ID LIKE ? THEN TO_DATE(SUBSTR(INSTRUCTION_ID, ?, ?), ?) WHEN INSTRUCTION_ID LIKE ? THEN TO_DATE(? ¦¦ SUBSTR(INSTRUCTION_ID, ?, ?), ?) ELSE CASE WHEN REGEXP_LIKE(SUBSTR(INSTRUCTION_ID, ?, ?), ?) THEN TO_DATE(SUBSTR(INSTR | 平均耗时(s)：25.49 | 执行次数：92 | 总耗时(s)：2344.68 | 监测时间：2026-04-20~2026-04-26 |  |  | 计划7.9版本修复 | 归档指令增量同步定时任务：获取待同步的增量指令 | com.cib.assets.settlement.payment.sharding.dao.IInstructionDODao.queryPeddingData |  |  | 钟继炜 | 2026-07-30 |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 按期填报 |  | 38天后截止 | 2026-04-28 09:29:59 | 2026-06-11 14:18:19 | [7 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-000758 | JSZL-202512220001 | 指令表 | SELECT DISTINCT I.INSTRUCTION_ID, I.PAYMENT_TYPE_ID FROM INSTRUCTION I,INSTRUCTION_EXT IE WHERE TRUNC(I.PAYMENT_AT) = TRUNC(SYSDATE) AND I.PAYMENT_TYPE_ID = ? AND I.PAYMENT_STATUS = ? AND ((IE.INSTRUCTION_PARAM_NAME = ? AND IE.INSTRUCTION_PARAM_VALUE = ?) OR (IE.INSTRUCTION_PARAM_NAME = ? AND IE.INSTRUCTION_PARAM_VALUE = ?)) AND EXISTS(SELECT ? FROM INSTRUCTION A,INSTRUCTION_EXT B WHERE B.INSTRUCTION_PARAM_NAME = ? AND B.INSTRUCTION_PARAM_VALUE = ? AND A.INSTRUCTION_ID = B.INSTRUCTION_ID AND I.INSTRUCTION_ID = A.INSTRUCTION_ID) AND NOT EXISTS(SELECT ? FROM INSTRUCTION A,INSTRUCTION_EXT B WHERE B.INSTRUCTION_PARAM_NAME = ? AND B.INSTRUCTION_PARAM_VALUE = ? AND A.INSTRUCTION_ID = B.INSTRUCTION_ID AND I.INSTRUCTION_ID = A.INSTRUCTION_ID) AND I.PAYMENT_MODE = ? AND (DISCARD_FLAG != ? OR DISCARD_FLAG IS NULL) AND I.INSTRUCTION_ID = IE.INSTRUCTION_ID UNION ALL SELECT T.TRADE_ID INSTRUCTION_ID, T.TRAN_TYPE PAYMENT_TYPE_ID FROM TRADE_BASE T WHERE T.TRAN_TYPE IN (?,?) AND TRADE_DATE = TRUNC(SYSDATE) AND INFORM_BROKER_STATUS = ? AND (DISCARD_FLAG != ? OR DISCARD_FLAG IS NULL) AND T.INFORM_WAY = ? UNION ALL SELECT T.TRADE_ID INSTRUCTION_ID, T.TRAN_TYPE PAYMENT_TYPE_ID FROM TRADE_BASE T WHERE T.TRAN_TYPE IN (?,?) AND TRADE_DATE = TRUNC(SYSDATE) AND INFORM_MANAGER_STATUS = ? AND T.INFORM_WAY = ? | 平均耗时(s)：8.25 | 执行次数：19943 | 总耗时(s)：164551.99 | 监测时间：2026-03-30~2026-04-05 |  |  | 计划7.9版本修复 | 类QFII定时通知券商与管理人定时任务：获取类QFII通知失败的指令 | com.cib.settlement.hkgl.qszf.dao.StmtPaymentDao.queryInformFailed | 1.类QFII定时通知券商与管理人定时任务，将每分钟执行改为每10分钟执行一次； 2.未命中索引，目前支付日期不再包含时分秒，将trunc(i.payment_at)中的trunc去掉； | StmtPaymentDao.queryInformFailed_v4.14.1 | 覃淞俊 | 2026-07-30 |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 按期填报 |  | 38天后截止 | 2026-04-13 15:26:47 | 2026-06-11 14:18:51 | [7 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-000752 | JSZL-202512220001 | 指令表 | WITH E_INSTRUCTION_EXT AS ( SELECT EX.GENERATE, EX.MANAGER_ID, EX.PRODUCT_CODE, EX.INSTRUCTION_NUM, EX.INSTRUCTION_MODEL, EX.MANAGER_ID ¦¦ EX.INSTRUCTION_NUM ¦¦ EX.GENERATE AS BUSINESS_ID1, NULL AS BUSINESS_ID2 FROM INSTRUCTION I JOIN INSTRUCTION_DISTINCT D ON D.INSTRUCTION_ID = I.INSTRUCTION_ID JOIN PRODUCT P ON I.PRODUCT_ID = P.PRODUCT_ID JOIN EC_INSTRUCTION EX ON D.SOURCE_ID=? AND (I.MANAGER_ID = EX.MANAGER_ID OR EX.GENERATE = ?) AND D.BUSINESS_ID = EX.MANAGER_ID ¦¦ EX.INSTRUCTION_NUM ¦¦ EX.GENERATE AND (EX.INSTRUCTION_MODEL= ? OR EX.GENERATE = ?) WHERE ((I.UPDATED_AT IS NULL AND I.CREATED_AT &gt;= TO_DATE(:1 , ?)) OR (I.UPDATED_AT &gt;= TO_DATE(:2 , ?))) AND I.ACTION_STATUS IS NOT NULL AND NOT EXISTS (SELECT ? FROM INSTRUCTION_INFOEM II WHERE II.INSTRUCTION_ID = I.INSTRUCTION_ID AND II.INSTRUCTION_STATUS = I.ACTION_STATUS AND (II.REALTIME_STATUS = I.FINAL_PAYMENTSTATUS OR I.FINAL_PAYMENTSTATUS IS NULL) AND (II.PAYMENT_STATUS = I.PAYMENT_STATUS OR I.PAYMENT_STATUS IS NULL) AND (II.PUSH_ZLPT = ? OR II.PUSH_ZLPT IS NULL OR (II.PUSH_ZLPT = ? AND II.ZLPT_FAIL_NUM &gt; :3 )) AND (II.PUSH_TYMH = ? OR II.PUSH_TYMH IS NULL OR (II.PUSH_TYMH = ? AND II.TYMH_FAIL_NUM &gt; :4 )) AND (II.PUSH_TGT = ? OR II.PUSH_TGT IS NULL OR (II.PUSH_TGT = ? AND II.TGT_FAIL_NUM &gt; :5 )) AND (II.PUSH_KSH = ? OR II.PUSH_KSH IS NULL OR (II.PUSH_KSH = ? AND II.KSH_FAIL_NUM &gt; :6 )) ) UNION ALL SELECT EX.GENERATE, EX.MANAGER_ID, EX.PRODUCT_CODE, EX.INSTRUCTION_NUM, EX.INSTRUCTION_MODEL, NULL AS BUSINESS_ID1, EX.PRODUCT_CODE ¦¦ EX.INSTRUCTION_NUM ¦¦ EX.GENERATE AS BUSINESS_ID2 FROM INSTRUCTION I JOIN INSTRUCTION_DISTINCT D ON D.INSTRUCTION_ID = I.INSTRUCTION_ID JOIN PRODUCT P ON I.PRODUCT_ID = P.PRODUCT_ID JOIN EC_INSTRUCTION EX ON D.SOURCE_ID=? AND P.PRODUCT_CODE = EX.PRODUCT_CODE AND D.BUSINESS_ID = EX.PRODUCT_CODE ¦¦ EX.INSTRUCTION_NUM ¦¦ EX.GENERATE AND ((EX.INSTRUCTION_MODEL &lt;&gt; ? OR EX.INSTRUCTION_MODEL IS NULL) AND EX.GENERATE &lt;&gt; ?) WHERE ((I.UPDATED_AT IS NULL AND I.CREATED_AT &gt;= TO_DATE(:7 , ?)) OR (I.UPDATED_AT &gt;= TO_DATE(:8 , ?))) AND I.ACTION_STATUS IS NOT NULL AND NOT EXISTS (SELECT ? FROM INSTRUCTION_INFOEM II WHERE II.INSTRUCTION_ID = I.INSTRUCTION_ID AND II.INSTRUCTION_STATUS = I.ACTION_STATUS AND (II.REALTIME_STATUS = I.FINAL_PAYMENTSTATUS OR I.FINAL_PAYMENTSTATUS IS NULL) AND (II.PAYMENT_STATUS = I.PAYMENT_STATUS OR I.PAYMENT_STATUS IS NULL) AND (II.PUSH_ZLPT = ? OR II.PUSH_ZLPT IS NULL OR (II.PUSH_ZLPT = ? AND II.ZLPT_FAIL_NUM &gt; :9 )) AND (II.PUSH_TYMH = ? OR II.PUSH_TYMH IS NULL OR (II.PUSH_TYMH = ? AND II.TYMH_FAIL_NUM &gt; :10 )) AN | 平均耗时(s)：24.53 | 执行次数：18051 | 总耗时(s)：442822.59 | 监测时间：2026-03-30~2026-04-05 |  |  | 计划7.9版本修复 | 指令变动通知定时任务：获取待通知的指令 | com.cib.settlement.api.dzzlpt.dao.ISourceInstructionDao.findInstructionInfosNewKsh | 1.未命中索引，将创建时间与更新时间字段的判断调整写法为函数索引：NVL(updated_at,created_at); 2.考虑将sql拆分多段，其中电子指令部分从主sql拆分，单独执行，再通过java代码拼接； | FindInstructionInfos_v4.14.1 | 郭亮亮 | 2026-07-30 |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 按期填报 |  | 38天后截止 | 2026-04-13 15:29:03 | 2026-06-11 14:18:34 | [7 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-000318 | JSZL-202512220001 | 与第9行重复 | SELECT * FROM ( SELECT ROW_.*, ROWNUM AS ROWNUM_ FROM ( WITH INSTRUCTION_DATA AS ( SELECT INSTRUCTION_ID,PRODUCT_ID,PAYMENT_DATE,PAYMENT_TYPE_ID,DIRECTION,AMOUNT,PAYMENT_REASON,SOURCE_ID,CREDIT_ACCOUNT,CREDIT_ACCOUNT_NAME,DEBIT_ACCOUNT,DEBIT_ACCOUNT_NAME,BANK_ID,BANK_NAME,BATCH,ENTRUST,IPO_SUBSCRIBE,WFID,WFSID,ITERATIONID,POSITION,P_INSTRUCTION_ID,PAYMENT_STATUS,ACTION_STATUS,PAYMENT_MODE,PAYMENT_AT,INTER_BANK,SAME_CITY,MESSAGE,CREATED_AT,CREATED_BY,UPDATED_AT,UPDATED_BY,INSTRUCTION_TYPE,CONCENTRATE_STATUS,VALIDATED_BY,USE_ID,PLUSTYPE,OUT_INSTRUCTION_ID,SECURITY_CODE,FBANK_ID,FBANK_NAME,FDQH,FJGH,SDQH,SJGH,DB_PRODUCT_ID,REALTIME_STATUS,PARENT_INSTRUCTION_ID,CREDIT_ACCT_TYPE_ID,DEBIT_ACCT_TYPE_ID,CREDIT_ACCOUNT_ID,DEBIT_ACCOUNT_ID,CURRENCY,WITHDRAW,VOUCHER,BUSINESS_TYPE,CASH,CREDIT_CARD,POST_ROUTE,PAYMENT_LEVEL,BUSINESS_SUBJECT,SUMMARY,CUSTOM_TYPE,BUSINESS_CATEGORY,CHANNEL,ACCOUNT_VOUCHER,ACCOUNT_PASSWORD,FUTHER_CODE,FUTHER_PASSWORD,CORE_INTERFACE,COUNTER_CASHFLOW,QSXWH,WXFXZYXX,INTERFACE_CODE,HSBZ,SUB_TYPE_ID,MESSAGE_V,ZQZH,ZQDM,RETURN_MSG,AUTOPAY,TRADE_TYPE,INSTR_GEN_SOURCE,ENTERACCOUNT_FLAG,LOCK_STATUS,ROLE_ID,CORE_MSG,FINAL_PAYMENTSTATUS,ZTCZFJG,LDSJMS,KH_PAYMENTSTATUS,CORE_INSTRUCTION_TYPE,CFCS,BEIYONG1,ZLSCFSJ,SHOWCOMEACCOUNT,PAYMENTWAY,FAXPUSHTIME,NEXTDATEINSTRUCTIONID,INSTRUC_BATCH,INSTRUC_BATCH_FLAG,INSTRUC_BATCH_SUM,INSTRUC_BATCH_DETAIL,USER_SUBSIDIARY_ORGAN,ZYZXRETFAXTIME,ZYZXRETMSG,ZYZXBZ,ACTIVITY_CENTER_STATUS,ACTIVITY_CENTER_FLAG,ACTIVITY_CENTER_MESSAGE,YWLSH,ZJTZZH,QHGSDM,INSTR_JBR,INSTR_FHR,BATCHINSNO,SUCCESSFUL_PAID_AT,PAY_LOCK_STATUS,PAY_LOCK_USER,REMARK,TGT_QDZLBH,AUTO_REMARK,IS_EMERGENCY_PAYMENT,TIMESTAMP,DISCARD_FLAG,PRIORITY,DB_STATUS,WHITE_FLGE,MZBZ,EXPORT_FLAG,PROIORITY_SUB,CSDS_BUSINESS_TYPE,WHETHER_PASS_AUXILIARY,AUXILIARY_ACCOUNT,VIRTUAL_PRODUCT_NAME,DEAL_ORG_NO,INSTRUCTION_MODEL,OUT_ORG_NO,CUST_PRD_CODE,CUST_CANCEL_STATUS,CUST_PRD_NAME,MANAGER_ID,PAYFLG,CORE_INSTRUCTION_ID,DFKSSJ,SUPERVISION_SIGN,SUPERVISORY_OPINION,INSTRUC_CONTACTS,DIRECT_STATUS,ANO_SYS_STAT,ARCHIVED_STATUS,ARCHIVED_RESULT,ARCHIVED_DATE,ARCHIVED_PACKAGE, CASE WHEN INSTRUCTION_ID LIKE ? THEN TO_DATE(? ¦¦ SUBSTR(INSTRUCTION_ID, ?, ?), ?) WHEN INSTRUCTION_ID LIKE ? THEN TO_DATE(SUBSTR(INSTRUCTION_ID, ?, ?), ?) WHEN INSTRUCTION_ID LIKE ? THEN TO_DATE(SUBSTR(INSTRUCTION_ID, ?, ?), ?) WHEN INSTRUCTION_ID LIKE ? THEN TO_DATE(SUBSTR(INSTRUCTION_ID, ?, ?), ?) ELSE CASE WHEN REGEXP_LIKE(SUBSTR(INSTRUCTION_ID, ?, ?), ?) THEN TO_DATE(SUBSTR(INSTRUCTION_ID, ?, ?), ?) ELSE NULL END END AS EXTRACTED_DATE FROM INSTRUCTION I WH | 平均耗时(s)：69.91 | 执行次数：132 | 总耗时(s)：9228.5 | 监测时间：2026-03-30~2026-04-05 |  |  | 计划7.9版本修复（重复） |  |  |  |  | 覃淞俊 | 2026-07-30 |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 按期填报 |  | 38天后截止 | 2026-04-13 15:27:26 | 2026-06-11 14:17:45 | [7 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-001459 | JSZL-202512220001 | 银行间合同表 | SELECT * FROM ( SELECT ROW_.*, ROWNUM AS ROWNUM_ FROM ( SELECT T.MARKET_TYPE , T.DATE_TYPE , T.BUSINESS_TYPE,T.CONTRACT_STATUS, T.OUR_STATUS , T.DEAL_ID , T.INIT_SETTLE_AMOUNT , T.SETTLEMENT_DATE , T.PRODUCT_ID ,T.PRODUCT_NAME, T.OPDCONFIRMSTATUS,T.SIUATIONEXPLAIN,T.SIUATIONDATE,T.SIUATIONBY,T.SIUATIONBRANCH, T.OPD_BRANCH, T.IND_BRANCH, (SELECT D.JGMC FROM IP_UNIT_STMT D WHERE T.IND_BRANCH=D.ZJ) AS IND_BRANCHID, (SELECT G.JGMC FROM IP_UNIT_STMT G WHERE T.OPD_BRANCH=G.ZJ) AS OPD_BRANCHID, T.INSTRID FROM ( SELECT (SELECT MBTMZ FROM IP_CODEINFO WHERE SJLX = (SELECT ZJ FROM IP_CODETYPE WHERE SJLXBH = ?) AND MBLXBH = CI.MARKET_TYPE) AS MARKET_TYPE, ? AS DATE_TYPE, (SELECT MBTMZ FROM IP_CODEINFO WHERE SJLX = (SELECT ZJ FROM IP_CODETYPE WHERE SJLXBH = ?) AND MBLXBH = CI.BUSINESS_TYPE) AS BUSINESS_TYPE, ? AS CONTRACT_STATUS, (SELECT MBTMZ FROM IP_CODEINFO WHERE SJLX = (SELECT ZJ FROM IP_CODETYPE WHERE SJLXBH = ?) AND MBLXBH = DECODE(CI.ACCOUNT_TYPE,?,CI.OUR_STATUS,CI.COUNTER_STATUS)) AS OUR_STATUS, CI.DEAL_ID AS DEAL_ID, CI.INIT_SETTLE_AMOUNT AS INIT_SETTLE_AMOUNT, NVL(CI.DELIVER_DATE1,CI.DELIVER_DATE2) AS SETTLEMENT_DATE, CI.PRODUCT_ID AS PRODUCT_ID, CI.PRODUCT_NAME AS PRODUCT_NAME, NVL(CM.OPD_CONFIRM_STATUS,?) AS OPDCONFIRMSTATUS, CM.SIUATION_EXPLAIN AS SIUATIONEXPLAIN, TO_CHAR(CM.SIUATION_DATE,?) AS SIUATIONDATE, (SELECT D.YHMC FROM IP_STAFF_STMT D WHERE CM.SIUATION_BY= D.YHBH) AS SIUATIONBY, CM.OPD_BRANCH AS SIUATIONBRANCH, PP.OPD_BRANCHID AS OPD_BRANCH, PP.IND_BRANCHID AS IND_BRANCH, CI.INSTR_ID AS INSTRID FROM CSBS_INSTRUCTION CI LEFT JOIN CRITICAL_MONITOR_SIGN CM ON CI.INSTR_ID = CM.RELATION_ID LEFT JOIN PRODUCT PP ON CI.PRODUCT_ID = PP.PRODUCT_CODE WHERE CI.INSTR_STATUS = ? AND CM.OPD_CONFIRM_STATUS IS NULL AND ( CI.DELIVER_DATE1 BETWEEN :1 AND :2 ) AND CI.PRODUCT_ID IN ( SELECT P1.PRODUCT_CODE FROM PRODUCT P1 WHERE P1.OPD_BRANCHID IN ( :3 ) ) UNION ALL SELECT (SELECT MBTMZ FROM IP_CODEINFO WHERE SJLX = (SELECT ZJ FROM IP_CODETYPE WHERE SJLXBH = ?) AND MBLXBH = CI.MARKET_TYPE) AS MARKET_TYPE, ? AS DATE_TYPE, (SELECT MBTMZ FROM IP_CODEINFO WHERE SJLX = (SELECT ZJ FROM IP_CODETYPE WHERE SJLXBH = ?) AND MBLXBH = CI.BUSINESS_TYPE) AS BUSINESS_TYPE, ? AS CONTRACT_STATUS, (SELECT MBTMZ FROM IP_CODEINFO WHERE SJLX = (SELECT ZJ FROM IP_CODETYPE WHERE SJLXBH = ?) AND MBLXBH = DECODE(CI.ACCOUNT_TYPE,?,CI.OUR_STATUS,CI.COUNTER_STATUS)) AS OUR_STATUS, CI.DEAL_ID AS DEAL_ID, CI.INIT_SETTLE_AMOUNT AS INIT_SETTLE_AMOUNT, NVL(CI.DELIVER_DATE1,CI.DELIVER_DATE2) AS SETTLEMENT_DATE, NULL AS PRODUCT_ID, NULL AS PRODUCT_NAME, | 平均耗时(s)：6.60 | 执行次数：308 | 总耗时(s)：2031.74 | 监测时间：2026-05-11~2026-05-17 |  |  | 计划7.9版本修复 | 关键时点监控页面-银行间结算状态监控：获取待确认的指令或未完成的银行间结算合同 | com.cib.settlement.hkgl.gjsdjk.dao.ICriticalJunctureMonitorDao.queryyhjjsInfoNew | 合同查询中的SETTLEMENT_DATE、finishdate查询条件写法未命中索引，需拆分为union拼接这两个查询结果 | queryyhjjsInfoCount | 覃淞俊 | 2026-07-31 |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 按期填报 |  | 39天后截止 | 2026-05-22 14:58:54 | 2026-06-10 14:13:17 | [7 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-002039 | JSZL-202512220001 | 新出现、指令表 | SELECT ( SELECT COUNT(*) FROM INSTRUCTION Z LEFT JOIN (SELECT P.PRODUCT_ID, P.PRODUCT_CODE, P.PRODUCT_NAME, P.MANAGER_ID, P.IND_BRANCHID, P.OPD_BRANCHID, P.OPERATION_MODE, (SELECT EXTERNAL_AGENCY_NAME FROM EXTERNAL_AGENCY EA WHERE EA.EXTERNAL_AGENCY_ID = P.MANAGER_ID AND EA.EFFECTSTATUS = ?) GLR FROM PRODUCT P WHERE P.PRODUCT_ID IN (SELECT AP.PRODUCT_ID FROM ACCOUNT_PRODUCT AP, BANK_ACCOUNT BA WHERE AP.BANK_ACCOUNT_ID = BA.BANK_ACCOUNT_ID AND BA.EFFECTSTATUS = ?) OR P.PRODUCT_ID IN (SELECT AUP.PRODUCT_ID FROM AUXILIARY_PRODUCT AUP, BANK_ACCOUNT BA WHERE BA.EFFECTSTATUS = ? AND AUP.EFFECTSTATUS = ? AND AUP.BANK_ACCOUNT_ID = BA.BANK_ACCOUNT_ID) UNION SELECT P.PRODUCT_ID, P.PRODUCT_CODE, P.PRODUCT_NAME, P.MANAGER_ID, P.IND_BRANCHID, P.OPD_BRANCHID, P.OPERATION_MODE, (SELECT EXTERNAL_AGENCY_NAME FROM EXTERNAL_AGENCY EA WHERE EA.EXTERNAL_AGENCY_ID = P.MANAGER_ID AND EA.EFFECTSTATUS = ?) GLR FROM PRODUCT P WHERE P.PRODUCT_TYPE_ID = ?) P ON Z.PRODUCT_ID = P.PRODUCT_ID WHERE ? = ? AND Z.INSTRUC_BATCH_FLAG IN (?, ?) AND Z.INSTRUCTION_MODEL != ? AND Z.PRODUCT_ID IS NOT NULL AND (Z.PAYMENT_TYPE_ID IS NULL OR Z.PAYMENT_TYPE_ID != ? OR (Z.PAYMENT_TYPE_ID = ? AND Z.CSDS_BUSINESS_TYPE IS NULL AND Z.SOURCE_ID = ?) OR (Z.PAYMENT_TYPE_ID = ? AND Z.SOURCE_ID = ?)) AND P.PRODUCT_ID IN (SELECT P.PRODUCT_ID FROM PRODUCT P, USER_INFO_BRANCH UIB WHERE UIB.USERID = :1 AND UIB.EFFECTSTATUS = ? AND P.IND_BRANCHID = UIB.BRANCHID UNION ALL SELECT P.PRODUCT_ID FROM PRODUCT P, USER_OPERATING_BRANCH OPD WHERE OPD.USERID = :2 AND OPD.EFFECTSTATUS = ? AND P.OPD_BRANCHID = OPD.BRANCHID) AND Z.PAYMENT_AT >= TRUNC(CAST(:3 AS TIMESTAMP)) AND Z.PAYMENT_AT < TRUNC(CAST(:4 AS TIMESTAMP) + ?) AND Z.PRODUCT_ID IN (:5 ) AND Z.PRODUCT_ID IN (SELECT PIB.PRODUCT_ID FROM PRODUCT_INFO_BRANCH PIB WHERE PIB.ROLEID = (SELECT IRS.JSBH FROM IP_ROLE_STMT IRS WHERE IRS.JSMC = ?) AND PIB.USERID IN (:6 )) AND (Z.PRODUCT_ID IS NULL OR NVL((SELECT PSI.SYSTEM_FLAG FROM PROD_SWITCH_INFO PSI WHERE PSI.PRODUCT_ID = Z.PRODUCT_ID), ?) = :7 ) ) + ( SELECT COUNT(*) FROM INSTRUCTION_2026 Z LEFT JOIN (SELECT P.PRODUCT_ID, P.PRODUCT_CODE, P.PRODUCT_NAME, P.MANAGER_ID, P.IND_BRANCHID, P.OPD_BRANCHID, P.OPERATION_MODE, (SELECT EXTERNAL_AGENCY_NAME FROM EXTERNAL_AGENCY EA WHERE EA.EXTERNAL_AGENCY_ID = P.MANAGER_ID AND EA.EFFECTSTATUS = ?) GLR FROM PRODUCT P WHERE P.PRODUCT_ID IN (SELECT AP.PRODUCT_ID FROM ACCOUNT_PRODUCT AP, BANK_ACCOUNT BA WHERE AP.BANK_ACCOUNT_ID = BA.BANK_ACCOUNT_ID AND BA.EFFECTSTATUS = ?) OR P.PRODUCT_ID IN (SELECT AUP.PRODUCT_ID FROM AUXILIARY_PRODUCT AUP | 平均耗时(s)：19.61 | 执行次数：117 | 总耗时(s)：2294.92 | 监测时间：2026-06-08~2026-06-14 |  |  | 计划7.9版本修复 | 指令流程查询页面：查找单产品指令数量 | com.cib.settlement.hkgl.zlcx.dao.IInstructionQueryDao.findQueryAllInfosForPtCountWithSingleProduct |  | type: slowSqlOptimization_20260709 name: instructionQuery | 朱永琦 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 192天后截止 | [10 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-002038 | JSZL-202512220001 | 新出现、指令表 | SELECT * FROM ( SELECT ROW_.*, ROWNUM AS ROWNUM_ FROM ( WITH BASE_INSTRUCTION AS (SELECT Z.INSTRUCTION_ID, (CASE WHEN (Z.SOURCE_ID IN(?,?,?,?,?) AND Z.PAYMENT_TYPE_ID IN (?,?)) THEN NVL((SELECT (CASE WHEN RTGS.SHCH_STOP_STATUS = ? THEN ? ELSE RTGS.SHCH_DRAW_STATUS END) ¦¦?¦¦ BY3 SHCH_DRAW_STATUS FROM RTGS_COLLECTION_RECORD_1 RTGS WHERE RTGS.INSTRUCTION_ID=Z.INSTRUCTION_ID),?) WHEN (Z.SOURCE_ID IN(?,?,?,?,?) AND Z.PAYMENT_TYPE_ID IN (?, ?)) THEN NVL((SELECT C.CCDC_DRAW_STATUS SHCH_DRAW_STATUS FROM CCDC_COLLECTION_RECORD C WHERE C.INSTRUCTION_ID=Z.INSTRUCTION_ID),?) WHEN (Z.SOURCE_ID IN(?,?,?) AND Z.PAYMENT_TYPE_ID IN (?,?)) THEN Z.DIRECT_STATUS WHEN (Z.PAYMENT_TYPE_ID =?) THEN NVL((SELECT INSTRUCTION_PARAM_VALUE FROM INSTRUCTION_EXT WHERE INSTRUCTION_ID = Z.INSTRUCTION_ID AND INSTRUCTION_PARAM_NAME =?),?) ELSE ? END) AS SHCHDRAWSTATUS, Z.PRODUCT_ID, Z.REALTIME_STATUS REALTIME_STATUS, Z.USE_ID, Z.PAYMENT_DATE, Z.PAYMENT_AT, Z.SUCCESSFUL_PAID_AT, Z.PAYMENT_TYPE_ID, (SELECT PT.PAYMENT_TYPE_NAME FROM PAYMENT_TYPE PT WHERE PT.PAYMENT_TYPE_ID = Z.PAYMENT_TYPE_ID) HKMC, Z.DIRECTION, Z.AMOUNT, Z.SOURCE_ID, Z.PAYMENT_REASON, Z.DEBIT_ACCOUNT, Z.DEBIT_ACCOUNT_NAME, Z.CREDIT_ACCOUNT, Z.CREDIT_ACCOUNT_NAME, Z.BANK_ID, Z.BANK_NAME, Z.DB_STATUS, Z.ANO_SYS_STAT, Z.BATCH, Z.IPO_SUBSCRIBE, Z.ENTRUST, Z.SECURITY_CODE, Z.PAYMENT_MODE, Z.INTER_BANK, DECODE(Z.FINAL_PAYMENTSTATUS, ?, ?, Z.FINAL_PAYMENTSTATUS) AS FINALSTATUSORDER, Z.FINAL_PAYMENTSTATUS, Z.PAYMENT_STATUS, (SELECT IP.YHMC FROM IP_STAFF_STMT IP WHERE IP.YHBH = Z.UPDATED_BY) UPDATEDBYNAME, Z.UPDATED_AT, Z.CREATED_AT, (SELECT IP.YHMC FROM IP_STAFF_STMT IP WHERE IP.YHBH = Z.INSTR_JBR) INSTR_JBR, (SELECT IP.YHMC FROM IP_STAFF_STMT IP WHERE IP.YHBH = Z.INSTR_FHR) INSTR_FHR, Z.FBANK_ID, Z.FBANK_NAME, Z.FDQH, Z.FJGH, Z.SDQH, Z.SJGH, Z.POST_ROUTE, Z.INSTRUC_BATCH, (SELECT W.WFNAME FROM WORKFLOW W WHERE W.WFID = Z.WFID) GZLMC, Z.SAME_CITY, Z.ZYZXRETFAXTIME, Z.ZYZXRETMSG, Z.ZYZXBZ, Z.INSTRUC_BATCH_FLAG, Z.ACTIVITY_CENTER_STATUS, Z.ACTIVITY_CENTER_FLAG, Z.ACTIVITY_CENTER_MESSAGE, NVL(Z.FAXPUSHTIME, Z.CREATED_AT) FAXPUSHTIME, Z.IS_EMERGENCY_PAYMENT, Z.TIMESTAMP, Z.PRIORITY, Z.SHOWCOMEACCOUNT, Z.PAYMENTWAY, Z.MESSAGE, Z.WHETHER_PASS_AUXILIARY, Z.TRADE_TYPE, Z.CORE_MSG, Z.CURRENCY BZ, Z.EXPORT_FLAG, Z.INSTRUCTION_TYPE, Z.ACTION_STATUS, Z.INSTRUCTION_MODEL, Z.DEAL_ORG_NO, (SELECT JGMC FROM IP_UNIT WHERE ZJ = Z.DEAL_ORG_NO) DEAL_ORG_NO_NAME, Z.CUST_CANCEL_STATUS, Z.CUST_PRD_CODE, Z.CUST_PRD_NAME, Z.OUT_ORG_NO, (SELECT JGMC FROM IP_UNIT WHERE ZJ = Z.OUT_ORG_NO) OUT_ORG_NO_NAME, Z.OU | 平均耗时(s)：3.09 | 执行次数：642 | 总耗时(s)：1985.24 | 监测时间：2026-06-08~2026-06-14 |  |  | 计划7.9版本修复 | 指令流程查询页面：查询普通指令列表 | com.cib.settlement.hkgl.zlcx.dao.IInstructionQueryDao.findAllInfosForPtNewYH1 |  | findAllInfosForPtCount_v4.14.1 | 覃淞俊 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 192天后截止 | [10 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-002027 | JSZL-202512220001 | 新出现、指令表 | SELECT * FROM ( SELECT ROW_.*, ROWNUM AS ROWNUM_ FROM ( SELECT * FROM ( SELECT Z.INSTRUCTION_ID, (CASE WHEN (Z.SOURCE_ID IN (?, ?, ?, ?, ?) AND Z.PAYMENT_TYPE_ID IN (?, ?)) THEN NVL((SELECT (CASE WHEN RTGS.SHCH_STOP_STATUS = ? THEN ? ELSE RTGS.SHCH_DRAW_STATUS END) ¦¦ ? ¦¦ BY3 SHCH_DRAW_STATUS FROM RTGS_COLLECTION_RECORD_1 RTGS WHERE RTGS.INSTRUCTION_ID = Z.INSTRUCTION_ID), ?) WHEN (Z.SOURCE_ID IN (?, ?, ?, ?, ?) AND Z.PAYMENT_TYPE_ID IN (?, ?)) THEN NVL((SELECT C.CCDC_DRAW_STATUS SHCH_DRAW_STATUS FROM CCDC_COLLECTION_RECORD C WHERE C.INSTRUCTION_ID = Z.INSTRUCTION_ID), ?) WHEN (Z.SOURCE_ID IN (?, ?, ?) AND Z.PAYMENT_TYPE_ID IN (?, ?)) THEN Z.DIRECT_STATUS WHEN (Z.PAYMENT_TYPE_ID = ?) THEN NVL((SELECT INSTRUCTION_PARAM_VALUE FROM INSTRUCTION_EXT WHERE INSTRUCTION_ID = Z.INSTRUCTION_ID AND INSTRUCTION_PARAM_NAME = ?), ?) ELSE ? END) AS SHCHDRAWSTATUS, Z.PRODUCT_ID, P.PRODUCT_CODE CPDM, P.PRODUCT_NAME CPMC, P.GLR, P.MANAGER_ID, (SELECT IP.JGMC FROM IP_UNIT_STMT IP WHERE IP.ZJ = P.OPD_BRANCHID) CPYYJG, P.OPERATION_MODE CPYYMS, P.OPD_BRANCHID OPDBRANCHID, P.IND_BRANCHID INDBRANCHID, Z.REALTIME_STATUS, Z.USE_ID, Z.PAYMENT_DATE, Z.PAYMENT_AT, Z.SUCCESSFUL_PAID_AT, Z.PAYMENT_TYPE_ID, (SELECT PT.PAYMENT_TYPE_NAME FROM PAYMENT_TYPE PT WHERE PT.PAYMENT_TYPE_ID = Z.PAYMENT_TYPE_ID) HKMC, Z.DIRECTION, Z.AMOUNT, Z.SOURCE_ID, Z.PAYMENT_REASON, Z.DEBIT_ACCOUNT, Z.DEBIT_ACCOUNT_NAME, Z.CREDIT_ACCOUNT, Z.CREDIT_ACCOUNT_NAME, Z.BANK_ID, Z.BANK_NAME, Z.DB_STATUS, Z.ANO_SYS_STAT, Z.BATCH, Z.IPO_SUBSCRIBE, Z.ENTRUST, Z.SECURITY_CODE, Z.PAYMENT_MODE, Z.INTER_BANK, Z.FINAL_PAYMENTSTATUS, Z.PAYMENT_STATUS, (SELECT IP.YHMC FROM IP_STAFF_STMT IP WHERE IP.YHBH = Z.UPDATED_BY) UPDATEDBYNAME, Z.UPDATED_AT, Z.CREATED_AT, (SELECT IP.YHMC FROM IP_STAFF_STMT IP WHERE IP.YHBH = Z.INSTR_JBR) INSTR_JBR, (SELECT IP.YHMC FROM IP_STAFF_STMT IP WHERE IP.YHBH = Z.INSTR_FHR) INSTR_FHR, Z.FBANK_ID, Z.FBANK_NAME, Z.FDQH, Z.FJGH, Z.SDQH, Z.SJGH, Z.POST_ROUTE, Z.INSTRUC_BATCH, (SELECT W.WFNAME FROM WORKFLOW W WHERE W.WFID = Z.WFID) GZLMC, Z.SAME_CITY, Z.ZYZXRETFAXTIME, Z.ZYZXRETMSG, Z.ZYZXBZ, Z.INSTRUC_BATCH_FLAG, Z.ACTIVITY_CENTER_STATUS, Z.ACTIVITY_CENTER_FLAG, Z.ACTIVITY_CENTER_MESSAGE, NVL(Z.FAXPUSHTIME, Z.CREATED_AT) FAXPUSHTIME, Z.IS_EMERGENCY_PAYMENT, Z.TIMESTAMP, Z.PRIORITY, Z.SHOWCOMEACCOUNT, Z.PAYMENTWAY, Z.MESSAGE, Z.WHETHER_PASS_AUXILIARY, Z.TRADE_TYPE, Z.CORE_MSG, Z.CURRENCY BZ, Z.EXPORT_FLAG, Z.INSTRUCTION_TYPE, Z.ACTION_STATUS, Z.INSTRUCTION_MODEL, Z.DEAL_ORG_NO, (SELECT JGMC FROM IP_UNIT WHERE ZJ = Z.DEAL_ORG_NO) DEAL_ORG_NO_NAME, Z.C | 平均耗时(s)：11.44 | 执行次数：164 | 总耗时(s)：1876.62 | 监测时间：2026-06-08~2026-06-14 |  |  | 计划7.9版本修复 | 指令流程查询页面：查找单产品指令列表 | com.cib.settlement.hkgl.zlcx.dao.IInstructionQueryDao.findQueryAllInfosForPtWithSingleProduct |  | type: slowSqlOptimization_20260709 name: instructionQuery | 朱永琦 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 192天后截止 | [10 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-001933 | JSZL-202512220001 | 新出现（高频）、已排25号版本 | SELECT I.INSTRUCTION_ID AS "instructionId", I.PAYMENT_TYPE_ID AS "paymentTypeId", E.GENERATE AS "sourceId", I.DIRECTION AS "direction", NULL AS "creditAcctTypeId", NULL AS "beiyong1", I.PAYMENT_AT AS "paymentAt" FROM INSTRUCTION I, EC_INSTRUCTION E, INSTRUCTION_EXT IE WHERE E.INSTRUCTION_ID = I.INSTRUCTION_ID AND I.INSTRUCTION_ID = IE.INSTRUCTION_ID AND I.PAYMENT_TYPE_ID = ? AND E.GENERATE = ? AND I.ACTION_STATUS = ? AND ((IE.INSTRUCTION_PARAM_NAME = ? AND IE.INSTRUCTION_PARAM_VALUE != ?) OR I.PAYMENT_STATUS = ?) AND I.PAYMENT_AT >= TRUNC(CAST(:1 AS TIMESTAMP)) UNION ALL SELECT I.INSTRUCTION_ID AS "instructionId", I.PAYMENT_TYPE_ID AS "paymentTypeId", E.GENERATE AS "sourceId", I.DIRECTION AS "direction", NULL AS "creditAcctTypeId", BA.EBNK_CUST_CD AS "beiyong1", I.PAYMENT_AT AS "paymentAt" FROM INSTRUCTION I LEFT JOIN CURDPT_ACCOUNT_PRODUCT BA ON I.CREDIT_ACCOUNT = BA.CUR_DPT_ACC_NO AND I.PRODUCT_ID = BA.CLR_PRD_ID LEFT JOIN EC_INSTRUCTION E ON E.INSTRUCTION_ID = I.INSTRUCTION_ID LEFT JOIN INSTRUCTION_EXT IE ON I.INSTRUCTION_ID = IE.INSTRUCTION_ID WHERE IE.INSTRUCTION_PARAM_NAME =? AND IE.INSTRUCTION_PARAM_VALUE =? AND I.PAYMENT_TYPE_ID = ? AND I.PAYMENT_AT >= TRUNC(CAST(:2 AS TIMESTAMP)) AND ROWNUM <=? | 平均耗时(s)：2.70 | 执行次数：1906 | 总耗时(s)：5148.64 | 监测时间：2026-06-08~2026-06-14 |  |  | 计划7.9版本修复 | 获取结构性存款已提交指令状态定时任务：该业务场景已取消，所以仅需删除 | com.cib.assets.settlement.instruction.dao.getUnpayJgxckInsList | 1.删除结构性存款逻辑，仅保留活期存款 2.不再关联电子指令表，拆分sql 3.关联指令扩展表调整，参考：findInstructionIdByChNew | updateJgxckInsList_V4.14.1 | 朱一晨 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 192天后截止 | [10 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-001932 | JSZL-202512220001 | 跑批 | INSERT INTO SETTLEMENT.JYZWXXWJ (HXJYLSBH,CPZXH,CPZNXH,JYRQ,JYSJ,XTSJC,ZDDH,JYDQDH,JYJGDH,JYDM,JZJYDM,JYFS,JYZL,JYGY,GYLSH,SQGY,QDZL,PZDH,PZQFRQ,KHDH,ZHDH,ZHCC,ZHLX,KHDQDH,KHJGDH,KMDH,CPDH,FWBH,HSDM,CQ,ZHYE,YEFX,JYJE,HBZL,XZBZ,JDBJ,ZJBS,CBBZ,BCZBZ,XJXMDH,QXRQ,PJ,RJBJ,KXHBZ,DJBBJ,RZZBJ,WHBZ,XZBJ,XZXH,FLBZ,YWCKH,ZYDH,BZ,JLZT) VALUES (:HXJYLSBH,:CPZXH,:CPZNXH,:JYRQ,:JYSJ,:XTSJC,:ZDDH,:JYDQDH,:JYJGDH,:JYDM,:JZJYDM,:JYFS,:JYZL,:JYGY,:GYLSH,:SQGY,:QDZL,:PZDH,:PZQFRQ,:KHDH,:ZHDH,:ZHCC,:ZHLX,:KHDQDH,:KHJGDH,:KMDH,:CPDH,:FWBH,:HSDM,:CQ,:ZHYE,:YEFX,:JYJE,:HBZL,:XZBZ,:JDBJ,:ZJBS,:CBBZ,:BCZBZ,:XJXMDH,:QXRQ,:PJ,:RJBJ,:KXHBZ,:DJBBJ,:RZZBJ,:WHBZ,:XZBJ,:XZXH,:FLBZ,:YWCKH,:ZYDH,SUBSTRB(:"BZ",?,LENGTHB(:"BZ")?),:JLZT) | 平均耗时(s)：1.18 | 执行次数：3598 | 总耗时(s)：4255.60 | 监测时间：2026-06-08~2026-06-14 |  |  | 计划7.9版本修复 | 批处理：导入核心JYZWXXWJ文件 |  | 减少插入字段数量，仅保留系统内使用的部分字段 |  | 郭亮亮 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 192天后截止 | [10 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-001931 | JSZL-202512220001 | 新出现 | SELECT CBA.BANK_ACCOUNT_ID AS "accountId", PRO.PRODUCT_ID ¦¦ ? ¦¦ BA.ACCOUNT_TYPE_ID AS "proAndType" FROM CORE_BANK_ACCOUNT CBA LEFT JOIN BANK_ACCOUNT BA ON CBA.BANK_ACCOUNT_ID = BA.BANK_ACCOUNT_ID LEFT JOIN (SELECT AP.BANK_ACCOUNT_ID, AP.PRODUCT_ID FROM ACCOUNT_PRODUCT AP, BANK_ACCOUNT BAI WHERE AP.BANK_ACCOUNT_ID = BAI.BANK_ACCOUNT_ID AND BAI.DEDICATED = ? AND AP.EFFECTSTATUS = ? AND NOT EXISTS( SELECT APS.BANK_ACCOUNT_ID FROM PRODUCT P , ACCOUNT_PRODUCT APS WHERE P.PRODUCT_ID = APS.PRODUCT_ID AND APS.BANK_ACCOUNT_ID = AP.BANK_ACCOUNT_ID AND P.EFFECTSTATUS = ? AND APS.EFFECTSTATUS = ? GROUP BY APS.BANK_ACCOUNT_ID HAVING COUNT(APS.BANK_ACCOUNT_ID)>? ) UNION ALL SELECT AP.BANK_ACCOUNT_ID, AP.PRODUCT_ID FROM ACCOUNT_PRODUCT AP, PRODUCT P, UNUSE_ACCT_INF UA WHERE AP.PRODUCT_ID = P.PRODUCT_ID AND AP.BANK_ACCOUNT_ID = UA.BANK_ACCOUNT_ID AND AP.EFFECTSTATUS = ? AND UA.EFFECTSTATUS = ? AND P.EFFECTSTATUS = ? ) PRO ON CBA.BANK_ACCOUNT_ID = PRO.BANK_ACCOUNT_ID WHERE LENGTH(CBA.BANK_ACCOUNT_ID) = ? AND NOT EXISTS (SELECT ? FROM ACCOUNT_PRODUCT AP, PRODUCT P, BANK_ACCOUNT BAT WHERE AP.PRODUCT_ID = P.PRODUCT_ID AND AP.EFFECTSTATUS = ? AND AP.BANK_ACCOUNT_ID = BAT.BANK_ACCOUNT_ID AND NVL(P.SUB_GROUP_MARK, ?) = ? AND BAT.DEDICATED = ? AND AP.BANK_ACCOUNT_ID = CBA.BANK_ACCOUNT_ID) | 平均耗时(s)：2.86 | 执行次数：5260 | 总耗时(s)：15021.38 | 监测时间：2026-06-08~2026-06-14 |  |  | 计划7.9版本修复 | 增量流水落地定时任务：获取全量账户以及关联的产品 | com.cib.settlement.api.lxgj.dao.ILxhxlsDao.queryAccByLxls | 需简化sql逻辑，将原sql拆分为多段执行，通过java代码再拼接最终数据。 原sql逻辑：获取所有独用账户（排除已绑定非小组合产品的共用账户）、以及关联的产品（1.当一个账户绑定多个产品时取空、已上线产品、未上线产品） |  | 王佳瑞 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 192天后截止 | [10 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-001926 | JSZL-202512220001 | 新出现、指令日间监控 | INSERT INTO INSTRUCTION_MONITOR (INSTRUCTION_ID,PRODUCT_ID,PAYMENT_TYPE_ID,ACTION_STATUS,PAYMENT_STATUS,UPDATED_AT,PAYMENT_AT,FINAL_PAYMENTSTATUS,DATA_TYPE,DIRECTION,CURRENCY,CREDIT_ACCOUNT,DEBIT_ACCOUNT,IS_EMERGENCY_PAYMENT, INSTRUCTION_MODEL,INSTRUCTION_TYPE,TRADE_TYPE,USE_ID,ROLE_ID,USER_SUBSIDIARY_ORGAN,DEAL_ORG_NO,OUT_ORG_NO,AMOUNT,INTER_BANK,CREATED_AT) (SELECT I.INSTRUCTION_ID, I.PRODUCT_ID, NVL((SELECT INSTRUCTION_PARAM_VALUE FROM INSTRUCTION_EXT WHERE INSTRUCTION_ID = I.INSTRUCTION_ID AND INSTRUCTION_PARAM_NAME = ?),I.PAYMENT_TYPE_ID) PAYMENTTYPEID, I.ACTION_STATUS, I.PAYMENT_STATUS, NVL(I.UPDATED_AT,I.CREATED_AT), I.PAYMENT_AT, I.FINAL_PAYMENTSTATUS, ? DATA_TYPE, I.DIRECTION, I.CURRENCY, I.CREDIT_ACCOUNT, I.DEBIT_ACCOUNT, I.IS_EMERGENCY_PAYMENT, I.INSTRUCTION_MODEL, I.INSTRUCTION_TYPE, I.TRADE_TYPE, I.USE_ID, I.ROLE_ID, I.USER_SUBSIDIARY_ORGAN, I.DEAL_ORG_NO, I.OUT_ORG_NO, I.AMOUNT, I.INTER_BANK, I.CREATED_AT FROM INSTRUCTION I WHERE I.CREATED_AT BETWEEN TRUNC(SYSDATE) AND TRUNC(SYSDATE)??/? AND I.DIRECTION = ? AND I.TRADE_TYPE = ? AND ((I.PAYMENTWAY != ?AND I.ACTION_STATUS != ?) OR (I.PAYMENTWAY = ? AND I.P_INSTRUCTION_ID = ?)) AND I.CREATED_AT < (SYSDATE?/?/?/?) ) | 平均耗时(s)：24.62 | 执行次数：1596 | 总耗时(s)：39292.16 | 监测时间：2026-06-08~2026-06-14 |  |  | 计划7.9版本修复 | 日间监控定时任务：保存首次接收提醒指令、大额头寸预报指令 | com.cib.settlement.common.jktx.dao.IMonitorReminderDataDao.insertFristInsMonitor、com.cib.settlement.common.jktx.dao.IMonitorReminderDataDao.insertBigInsMonitor | 添加索引字段过滤条件： #第一段：payment_date = trunc(sysdate) #第二段：payment_at >= trunc(sysdate) | InsertFristInsMonitor_v4.14.1 | 郭亮亮 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 192天后截止 | [10 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-001921 | JSZL-202512220001 | 新出现、指令日间监控 | WITH QX_SQL AS (SELECT WM_CONCAT(PRO_IND_BRANCHID) AS BRANCHID FROM CNZL_AUTHPAR WHERE INSTR(USER_BRANCHID, ?) > ? AND EFFECTSTATUS = ? AND FOUREYESSTATUS = ?), CHECK_NUM AS (SELECT COUNT(?) C FROM CNZL_AUTHPAR WHERE INSTR(PRO_IND_BRANCHID, ?) > ? AND EFFECTSTATUS = ? AND FOUREYESSTATUS = ?) SELECT Z.UNIT_ID, :1 USER_ID, Z.MON_MAT_TYPE, :2 REMINDER_TYPE, Z.DATA_AT, Z.INS_ID, NVL(Z.PRODUCT_ID, Z.UNIT_ID) AS PRODUCT_ID, NVL(Z.STEP_ID, ?) AS STEP_ID, (SELECT IR.CDBH FROM IP_RESMENU IR WHERE IR.CDURL = (CASE WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? ELSE ? END)) AS CDBH, NVL((SELECT PT.PAYMENT_TYPE_NAME FROM PAYMENT_TYPE PT WHERE Z.PAYMENT_TYPE_ID = PT.PAYMENT_TYPE_ID), NVL((SELECT IC.MBTMZ FROM IP_CODEINFO IC WHERE IC.SJLX IN (?, ?) AND IC.MBLXBH = Z.PAYMENT_TYPE_ID), ?)) AS PAYMENT_TYPE_NAME, (CASE WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? ELSE ? END) AS STEP_NAME, NVL(Z.PAYMENT_TYPE_ID, ?) AS PAYMENT_TYPE_ID, Z.DATA_TYPE, Z.TIME_OUT_FLAG FROM TIME_OUT_DATA Z WHERE Z.DATA_AT = TRUNC(SYSDATE) AND Z.MON_MAT_TYPE = :3 AND EXISTS (SELECT ? FROM DUAL WHERE (Z.STEP_ID = ? OR (Z.INSTRUCTION_MODEL = ? AND Z.STEP_ID IS NULL) ) AND EXISTS (SELECT ? FROM IP_BUTTON_LIST B, IP_RESMENU R WHERE B.CDBH = R.CDBH AND B.ACTION = ? AND R.CDURL = ? AND B.JSBH IN ( :4 , :5 , :6 , :7 , :8 ) AND EXISTS (SELECT ? FROM DUAL WHERE Z.DATA_TYPE = ? AND Z.USE_ID IN (?, :9 ) AND EXISTS ( SELECT ? FROM PRODUCT_INFO_BRANCH PIB WHERE PIB.PRODUCT_ID = Z.PRODUCT_ID AND PIB.USERID = :10 AND PIB.ROLEID = B.JSBH UNION ALL SELECT ? FROM PRODUCT P, USER_INFO_BRANCH UIB WHERE P.PRODUCT_ID = Z.PRODUCT_ID AND P.SUB_GROUP_MARK = ? AND P.IND_BRANCHID = UIB.BRANCHID AND UIB.USERID = :11 UNION ALL SELECT ? FROM DUAL WHERE Z.INSTRUCTION_MODEL = ? AND EXISTS ( SELECT ? FROM IP_STAFF IP,SAD_CC S WHERE S.BRANCHID = IP.SSJG AND IP.YHBH = :12 AND S.RANGE IN( SUBSTR( DECODE(Z.DIRECTION,?,Z.CREDIT_ACCOUNT,?,Z.DEBIT_ACCOUNT,?,Z.CREDIT_ACCOUNT),?,?), SUBSTR( DECODE(Z.DIRECTION,?,Z.CR | 平均耗时(s)：2.52 | 执行次数：1120 | 总耗时(s)：2817.84 | 监测时间：2026-06-08~2026-06-14 |  |  | 计划7.9版本修复 | 日间监控定时任务：获取待监控指令列表 | com.cib.settlement.common.jktx.dao.IMonitorReminderDataDao.getInsReminderCheckSad | 1.调整查询条件中DATA_AT、MON_MAT_TYPE顺序； 2.去除未上线信息经办、未上线核算经办、未上线核算复核、应急指令、信息审核； 3.其他指令工作流的每一步均拆分独立的sql，不再通过一条sql全部查询 | GetInsReminderCheckSad_v4.14.1 | 郭亮亮 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 192天后截止 | [10 empty] | 2025-12-01 | 2026-12-31 | 2026-12-31 | 公司级 | 慢SQL专项治理 | 常态化任务 |  | 一般 | 重要 | 研发标准执行 | 限期完成 |  | 徐朝阳/893552 | 研发管理部/开发标准管理团队
JSZL-202512220001-002202 | JSZL-202512220001 | 指令审核-AI审核指令 | MERGE INTO INSTRUCTION_AI_AUDIT_RESULT A USING( SELECT :1 AS INSTRUCTIONID, :2 AS AUDITRESULT, :3 AS EVALRATIONALE, :4 AS AICONTENT, :5 AS FAILREASON, :6 AS CREATEDBY, :7 AS AMOUNT, :8 AS PAYMENTAT, :9 AS PAYMENTTYPEID, :10 AS PRODUCTID FROM DUAL ) B ON(A.INSTRUCTION_ID = B.INSTRUCTIONID) WHEN NOT MATCHED THEN INSERT (INSTRUCTION_ID, AUDIT_RESULT, EVAL_RATIONALE, AI_CONTENT, CREATED_AT, CREATED_BY,AMOUNT,PAYMENT_AT,PAYMENT_TYPE_ID,PRODUCT_ID) VALUES (B.INSTRUCTIONID,B.AUDITRESULT,B.EVALRATIONALE,B.AICONTENT,CURRENT_TIMESTAMP,B.CREATEDBY,B.AMOUNT,B.PAYMENTAT,B.PAYMENTTYPEID,B.PRODUCTID) WHEN MATCHED THEN UPDATE SET A.AUDIT_RESULT = B.AUDITRESULT, A.EVAL_RATIONALE= B.EVALRATIONALE, A.AI_CONTENT= B.AICONTENT, A.FAIL_REASON = B.FAILREASON, A.UPDATED_AT = CURRENT_TIMESTAMP, A.AMOUNT = B.AMOUNT, A.PAYMENT_AT = B.PAYMENTAT, A.PAYMENT_TYPE_ID = B.PAYMENTTYPEID, A.PRODUCT_ID = B.PRODUCTID | 平均耗时(s)：5.42 | 执行次数：824 | 总耗时(s)：4468.34 | 监测时间：2026-06-15~2026-06-21 |  |  | 计划7.9版本修复 | 指令接入或指令审核页面：发起AI指令审核 | com.cib.settlement.hkgl.aiaudit.dao.IInstructionAiAuditResultDao.insertNew | 由于代码已判断是否存在，考虑将merge语句直接修改为insert语句，还有调整下代码中判断指令审核中的顺序 | AIinsertNew_V4.14.1 | 朱一晨 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 按期填报 |  | 13天后截止 | 2026-06-26 15:30 | 2026-06-26 15:30
JSZL-202512220001-002200 | JSZL-202512220001 | RTGS自动提款任务 | UPDATE RTGS_QSJSJG RQS SET RQS.SFKTK = ? WHERE RQS.SFKTK IS NULL | 平均耗时(s)：8.32 | 执行次数：495 | 总耗时(s)：4117.29 | 监测时间：2026-06-15~2026-06-21 |  |  | 计划7.9版本修复 | RTGS自动提款任务：更新是否可提款状态 | com.cib.settlement.hkgl.rtgsjygl.dao.IRtgsQsjsjgDao.updatektkAfterOptimize | 待确认：6月11日已下发，理论该sql已不存在，检查6月15日生产日志也没有，只有优化后的sql，再检查下巡检报告，上周一周的巡检报告也没有出现，待后续观察 |  |  |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 按期填报 |  | 35天后截止 | 2026-06-26 15:25 | 2026-06-26 15:25
JSZL-202512220001-002204 | JSZL-202512220001 | 一键清核联动自动任务 | SELECT QP2.* FROM ( SELECT QP.*, (SELECT P.PRODUCT_CODE FROM PRODUCT P WHERE P.EFFECTSTATUS = ? AND P.PRODUCT_ID = :1 ) AS PRODUCT_CODE, DECODE(QP.PAYMENT_RATE,?,TRUNC(CAST(:2 AS TIMESTAMP)),PKG_PUB.GET_DATE_AFTER(DECODE(QP.PAYMENT_RATE,?,?,?,?,QP.PAYMENT_RATE),QP.DATE_PROPERTY,QP.PAYMENT_DAY,?)) AS PAYMENT_AT, GET_IDS(QP.PRODUCT_ID) AS IDS FROM QHLD_PARAMETER QP WHERE QP.EFFECTSTATUS = ? AND QP.TERMINATE_FLAG != ? AND EXISTS (SELECT PC2.CODE_ID FROM (SELECT PC.CODE_ID,PC.PARA_KEY,PKG_PUB.GET_CONTAINT_ITEMS(:3 ,PC.CODE_ID) AS CON FROM PARA_CODE PC) PC2 WHERE PC2.PARA_KEY = QP.PRODUCT_ID AND PC2.CON IS NOT NULL) AND QP.PAYMENT_TYPE_ID = :4 ) QP2 WHERE QP2.IDS IS NOT NULL | 平均耗时(s)：1.09 | 执行次数：1826 | 总耗时(s)：1990.66 | 监测时间：2026-06-15~2026-06-21 |  |  | 计划7.9版本修复 | 一键清核联动定时任务：根据产品匹配清核联动参数 | com.cib.settlement.csgl.qhld.dao.IMatchQhldCreateInstructionDao.getMatchProductOpt | SQL优化示例： 1.简化产品条件匹配方式，取消函数调用； 2.删除get_ids函数调用以及判空条件； select qp.*, (SELECT p.PRODUCT_CODE FROM product p WHERE p.effectstatus = '1' AND p.PRODUCT_ID = #{productId}) AS PRODUCT_CODE, decode(qp.payment_rate,'0',trunc(cast(#{paymentDate} as timestamp)),PKG_PUB.get_date_after(decode(qp.payment_rate,'1','0','2','1',qp.payment_rate),qp.date_property,qp.payment_day,'1')) AS PAYMENT_AT from qhld_parameter qp WHERE qp.effectstatus = '1' AND qp.TERMINATE_FLAG != '1' AND qp.PRODUCT_ID IS NOT NULL AND exists (select 1 from para_code pc2 where pc2.para_key = qp.PRODUCT_ID and pc2.code_id = #{#{productId}}) <if test="paymentTypeId != null and paymentTypeId != ''"> and qp.PAYMENT_TYPE_ID = #{paymentTypeId}</if> <if test="isInsCheck != null and isInsCheck != ''"> and qp.IS_INS_CHECK = #{isInsCheck}</if> | SLOW_SQL_GTE_MATCH_SWITCH_V4.14.1 | 高志昭 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 188天后截止 |  |  | 2026-06-25 20:00
JSZL-202512220001-002203 | JSZL-202512220001 | RTGS自动提款任务 | SELECT R.* FROM RTGS_QSJSJG R WHERE R.YWLSH = :1 AND R.MARKET = :2 | 平均耗时(s)：2.70 | 执行次数：825 | 总耗时(s)：2228.77 | 监测时间：2026-06-15~2026-06-21 |  |  | 计划7.9版本修复（无需业务测试，回归即可） | 接收深圳RTGS或ETF报文接口：获取交收信息 | com.cib.settlement.hkgl.rtgsjygl.dao.IRtgsQsjsjgDao.lockQsjsjg、com.cib.settlement.hkgl.rtgsjygl.dao.IRtgsQsjsjgDao.queryRtgsQsjsjgInfoV4_13_0 | 未命中索引，考虑将YWLSH字段添加为索引字段 |  |  |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 188天后截止 |  |  | 2026-06-25 20:00
JSZL-202512220001-002201 | JSZL-202512220001 | 清理历史数据 | DELETE FROM INSTRUCTION_EXT II WHERE NOT EXISTS ( SELECT ? FROM INSTRUCTION SMI WHERE SMI.INSTRUCTION_ID = II.INSTRUCTION_ID ) AND ROWNUM <= ? | 平均耗时(s)：23.79 | 执行次数：104 | 总耗时(s)：2474.26 | 监测时间：2026-06-15~2026-06-21 |  |  | 计划7.9版本修复（无需业务测试，回归即可） | 清理历史指令扩展表数据定时任务：分批清理历史数据 | com.cib.assets.settlement.payment.sharding.dao.IInstructionExtDODao.deleteExtWithoutInstruction | 停止定时任务，后续不再使用 |  |  |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 188天后截止 |  |  | 2026-06-25 20:00
JSZL-202512220001-002199 | JSZL-202512220001 | 日间监控定时任务 | WITH QX_SQL AS (SELECT WM_CONCAT(PRO_IND_BRANCHID) AS BRANCHID FROM CNZL_AUTHPAR WHERE INSTR(USER_BRANCHID, ?) > ? AND EFFECTSTATUS = ? AND FOUREYESSTATUS = ?), CHECK_NUM AS (SELECT COUNT(?) C FROM CNZL_AUTHPAR WHERE INSTR(PRO_IND_BRANCHID, ?) > ? AND EFFECTSTATUS = ? AND FOUREYESSTATUS = ?) SELECT Z.UNIT_ID, :1 USER_ID, Z.MON_MAT_TYPE, :2 REMINDER_TYPE, Z.DATA_AT, Z.INS_ID, NVL(Z.PRODUCT_ID, Z.UNIT_ID) AS PRODUCT_ID, NVL(Z.STEP_ID, ?) AS STEP_ID, (SELECT IR.CDBH FROM IP_RESMENU IR WHERE IR.CDURL = (CASE WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? ELSE ? END)) AS CDBH, NVL((SELECT PT.PAYMENT_TYPE_NAME FROM PAYMENT_TYPE PT WHERE Z.PAYMENT_TYPE_ID = PT.PAYMENT_TYPE_ID), NVL((SELECT IC.MBTMZ FROM IP_CODEINFO IC WHERE IC.SJLX IN (?, ?) AND IC.MBLXBH = Z.PAYMENT_TYPE_ID), ?)) AS PAYMENT_TYPE_NAME, (CASE WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? ELSE ? END) AS STEP_NAME, NVL(Z.PAYMENT_TYPE_ID, ?) AS PAYMENT_TYPE_ID, Z.DATA_TYPE, Z.TIME_OUT_FLAG FROM TIME_OUT_DATA Z WHERE Z.DATA_AT = TRUNC(SYSDATE) AND Z.MON_MAT_TYPE = :3 AND EXISTS (SELECT ? FROM DUAL WHERE (Z.STEP_ID = ? OR (Z.INSTRUCTION_MODEL = ? AND Z.STEP_ID IS NULL) ) AND EXISTS (SELECT ? FROM IP_BUTTON_LIST B, IP_RESMENU R WHERE B.CDBH = R.CDBH AND B.ACTION = ? AND R.CDURL = ? AND B.JSBH IN ( :4 , :5 , :6 , :7 ) AND EXISTS (SELECT ? FROM DUAL WHERE Z.DATA_TYPE = ? AND Z.USE_ID IN (?, :8 ) AND EXISTS ( SELECT ? FROM PRODUCT_INFO_BRANCH PIB WHERE PIB.PRODUCT_ID = Z.PRODUCT_ID AND PIB.USERID = :9 AND PIB.ROLEID = B.JSBH UNION ALL SELECT ? FROM PRODUCT P, USER_INFO_BRANCH UIB WHERE P.PRODUCT_ID = Z.PRODUCT_ID AND P.SUB_GROUP_MARK = ? AND P.IND_BRANCHID = UIB.BRANCHID AND UIB.USERID = :10 UNION ALL SELECT ? FROM DUAL WHERE Z.INSTRUCTION_MODEL = ? AND EXISTS ( SELECT ? FROM IP_STAFF IP,SAD_CC S WHERE S.BRANCHID = IP.SSJG AND IP.YHBH = :11 AND S.RANGE IN( SUBSTR( DECODE(Z.DIRECTION,?,Z.CREDIT_ACCOUNT,?,Z.DEBIT_ACCOUNT,?,Z.CREDIT_ACCOUNT),?,?), SUBSTR( DECODE(Z.DIRECTION,?,Z.CREDIT_A | 平均耗时(s)：2.20 | 执行次数：1668 | 总耗时(s)：3674.24 | 监测时间：2026-06-15~2026-06-21 |  |  | 计划7.9版本修复（重复） | 日间监控定时任务：获取待监控指令列表 | com.cib.settlement.common.jktx.dao.IMonitorReminderDataDao.getInsReminderCheckSad | 同36行 |  | 郭亮亮 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 188天后截止 |  |  | 2026-06-25 20:00
JSZL-202512220001-002057 | JSZL-202512220001 | 日间监控定时任务 | WITH QX_SQL AS (SELECT WM_CONCAT(PRO_IND_BRANCHID) AS BRANCHID FROM CNZL_AUTHPAR WHERE INSTR(USER_BRANCHID, ?) > ? AND EFFECTSTATUS = ? AND FOUREYESSTATUS = ?), CHECK_NUM AS (SELECT COUNT(?) C FROM CNZL_AUTHPAR WHERE INSTR(PRO_IND_BRANCHID, ?) > ? AND EFFECTSTATUS = ? AND FOUREYESSTATUS = ?) SELECT Z.UNIT_ID, :1 USER_ID, Z.MON_MAT_TYPE, :2 REMINDER_TYPE, Z.DATA_AT, Z.INS_ID, NVL(Z.PRODUCT_ID, Z.UNIT_ID) AS PRODUCT_ID, NVL(Z.STEP_ID, ?) AS STEP_ID, (SELECT IR.CDBH FROM IP_RESMENU IR WHERE IR.CDURL = (CASE WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? ELSE ? END)) AS CDBH, NVL((SELECT PT.PAYMENT_TYPE_NAME FROM PAYMENT_TYPE PT WHERE Z.PAYMENT_TYPE_ID = PT.PAYMENT_TYPE_ID), NVL((SELECT IC.MBTMZ FROM IP_CODEINFO IC WHERE IC.SJLX IN (?, ?) AND IC.MBLXBH = Z.PAYMENT_TYPE_ID), ?)) AS PAYMENT_TYPE_NAME, (CASE WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? WHEN Z.STEP_ID = ? THEN ? ELSE ? END) AS STEP_NAME, NVL(Z.PAYMENT_TYPE_ID, ?) AS PAYMENT_TYPE_ID, Z.DATA_TYPE, Z.TIME_OUT_FLAG FROM TIME_OUT_DATA Z WHERE Z.DATA_AT = TRUNC(SYSDATE) AND Z.MON_MAT_TYPE = :3 AND EXISTS (SELECT ? FROM DUAL WHERE (Z.STEP_ID = ? OR (Z.INSTRUCTION_MODEL = ? AND Z.STEP_ID IS NULL) ) AND EXISTS (SELECT ? FROM IP_BUTTON_LIST B, IP_RESMENU R WHERE B.CDBH = R.CDBH AND B.ACTION = ? AND R.CDURL = ? AND B.JSBH IN ( :4 , :5 ) AND EXISTS (SELECT ? FROM DUAL WHERE Z.DATA_TYPE = ? AND Z.USE_ID IN (?, :6 ) AND EXISTS ( SELECT ? FROM PRODUCT_INFO_BRANCH PIB WHERE PIB.PRODUCT_ID = Z.PRODUCT_ID AND PIB.USERID = :7 AND PIB.ROLEID = B.JSBH UNION ALL SELECT ? FROM PRODUCT P, USER_INFO_BRANCH UIB WHERE P.PRODUCT_ID = Z.PRODUCT_ID AND P.SUB_GROUP_MARK = ? AND P.IND_BRANCHID = UIB.BRANCHID AND UIB.USERID = :8 UNION ALL SELECT ? FROM DUAL WHERE Z.INSTRUCTION_MODEL = ? AND EXISTS ( SELECT ? FROM IP_STAFF IP,SAD_CC S WHERE S.BRANCHID = IP.SSJG AND IP.YHBH = :9 AND S.RANGE IN( SUBSTR( DECODE(Z.DIRECTION,?,Z.CREDIT_ACCOUNT,?,Z.DEBIT_ACCOUNT,?,Z.CREDIT_ACCOUNT),?,?), SUBSTR( DECODE(Z.DIRECTION,?,Z.CREDIT_ACCOUNT,?,Z.D | 平均耗时(s)：1.14 | 执行次数：63916 | 总耗时(s)：73104.90 | 监测时间：2026-06-15~2026-06-21 |  |  | 计划7.9版本修复（重复） | 日间监控定时任务：获取待监控指令列表 | com.cib.settlement.common.jktx.dao.IMonitorReminderDataDao.getInsReminderCheckSad | 同36行 |  | 郭亮亮 |  |  | 按期开展中 | 未开始 |  | 0 |  |  |  | 未填报 | 188天后截止 |  |  | 2026-06-25 20:00